## Iteration 1
Story/Task | Time | Developer | Story/Task | Time | Developer
System Location |  |  | System Cost
Write validation tests | 0.5 | Alvis | Write validation tests | 0.5 | Alvis
Add interface elements | 0.5/1 | Cherry/Dane | Add interface elements | 0.5/0.5 | Cherry/Dane
Add javascript | 5 | Dane | Story Points: 1 | 1.5
Story Points: 2 | 7
Panels and Orientations
System Size |  |  | Write validation tests | 0.5/0.5 | Alvis/Dane
Write validation tests | 0.5/0.5 | Alvis/Dane | Add methods to build drop-down lists | 2 | Dane
Add method to build drop-down list | 2 | Dane | Add interface elements | 0.5/1 | Cherry/Dane
Add interface elements | 0.5/1 | Cherry/Dane | Add javascript | 8 | Dane
Add javascript | 2 | Dane | Story Points: 2 | 12.5
Story Points: 2 | 6.5
Electricity Usage
Hours of Sunlight |  |  | Write validation tests | 0.5 | Alvis
Write validation tests | 0.5/0.5 | Alvis/Dane | Add interface elements | 0.5/0.5 | Cherry/Dane
Add method to build drop-down list | 2 | Dane | Story Points: 1 | 1.5
Add interface elements | 0.5/0.5 | Cherry/Dane
Story Points: 1 | 4 |  | Input Validation
|  |  | Write tests | 1 | Alvis
Electricity Tariffs |  |  | Implement class for server-side input validation | 2 | Alvis
Write tests | 0.5 | Alvis | Story Points: 2 | 3
Add interface elements | 0.5/1 | Cherry/Dane
Add javascript | 5 | Dane
Story Points: 1 | 7

## Iteration 2
Story | Act. | Developer | Story | Act. | Developer
Electricity Tariff Increase |  |  | Daily Solar Generation
Write validation tests | 0.5 | Alvis | Write tests | 0.5 | Matthew
Add interface elements | 0.5/0.5 | Cherry/Dane | Implement class for calculation | 1 | Matthew
Story Points: 1 | 1.5 |  | Output results to page | 1 | Cherry
|  |  | Story Points: 1 | 2.5
Daily Solar Used
Write tests | 0.5 | Matthew | Annual Solar Generation
Implement class for calculation | 1 | Matthew | Write tests | 0.5 | Matthew
Output results to page | 1 | Cherry | Implement class for calculation | 1 | Matthew
Story Points: 1 | 2.5 |  | Output results to page | 1 | Cherry
|  |  | Story Points: 1 | 2.5
Simple Output
Store and retrieve information with Datastore | 6 | Cherry | Assumptions Made
Output information to page | 6 | Cherry | Add interface elements | 2 | Dane
Story Points: 2 | 12 |  | Add javascript | 5 | Dane
|  |  | Story Points: 1 | 7
Replacement Inverters
Write validation tests | 0.5 | Alvis | Desktop Application
Add interface elements | 0.5/1 | Cherry/Dane | Begin implementing interface | 10 | Cedric
Add javascript | 2 | Dane
Story Points: 1 | 4

## Charts
Velocity: 10