## Iteration 1
Story | Est. | Act. | Developer | Story | Est. | Act. | Developer
System Location |  |  | Shenchen Pan | System Cost |  |  | Dane Wilson
Write tests | 1 |  |  | Write tests | 1
Add fields for system location | 0.5 |  | done | Add field for system cost | 0.5
Add relevant data to database | 2 |  |  | Add input validation | 2
Implement geocoding and/or reverse geocoding | 2 |  |  | Run tests | 0.5
Add input validation | 2 |  | not needed | Story Points: 1 | 4
Run tests | 0.5
Story Points: 2 | 8 |  |  | Panels and Orientations
|  |  |  | Write tests | 2
System Size |  |  | Cedric Viney | Add fields for number of panels | 0.5
Write tests | 2 |  |  | Add drop-down lists for orientations | 1
Add drop-down list for system size | 1 |  |  | Add relevant data to database | 2
Add relevant data to database | 2 |  |  | Add input validation | 2
Add input validation | 2 |  |  | Run tests | 0.5
Run tests | 1 |  |  | Story Points: 2 | 8
Story Points: 2 | 8
Electricity Usage
Hours of Sunlight |  |  |  | Write tests | 1
Write tests | 1 |  |  | Add field for electricity usage | 0.5
Add field for hours of sunlight | 0.5 |  |  | Add input validation | 2
Add input validation | 2 |  |  | Run tests | 0.5
Run tests | 0.5 |  |  | Story Points: 1 | 4
Story Points: 1 | 4
Input Validation
Electricity Tariffs |  |  |  | Write tests | 1.5
Write tests | 1 |  |  | Add local input validation | 3
Add fields for electricity tariffs | 0.5 |  |  | Add server-side input validation | 3
Add input validation | 2 |  |  | Run tests | 0.5
Run tests | 0.5 |  |  | Story Points: 2 | 8
Story Points: 1 | 4

## Iteration 2
Story | Est. | Act. | Developer | Story | Est. | Act. | Developer
Electricity Tariff Increase |  |  |  | Daily Solar Generation
Write tests | 1 |  |  | Write tests | 1
Add field for electricity tariff increase | 2 |  |  | Implement calculations | 1.5
Add input validation | 0.5 |  |  | Format output | 1
Run tests | 0.5 |  |  | Run tests | 0.5
Story Points: 1 | 4 |  |  | Story Points: 1 | 4
Daily Solar Used |  |  |  | Daily Savings
Write tests | 1 |  |  | Write tests | 1
Implement calculations | 1.5 |  |  | Implement calculations | 1.5
Format output | 1 |  |  | Format output | 1
Run tests | 0.5 |  |  | Run tests | 0.5
Story Points: 1 | 4 |  |  | Story Points: 1 | 4
Annual Solar Generation |  |  |  | Annual Savings
Write tests | 1 |  |  | Write tests | 1
Implement calculations | 1.5 |  |  | Implement calculations | 1.5
Format output | 1 |  |  | Format output | 1
Run tests | 0.5 |  |  | Run tests | 0.5
Story Points: 1 | 4 |  |  | Story Points: 1 | 4
Cumulative Savings |  |  |  | Simple Output
Write tests | 1 |  |  | Write tests | 1
Implement calculations | 1.5 |  |  | Separate simple output from advanced output | 6.5
Format output | 1 |  |  | Run tests | 0.5
Run tests | 0.5 |  |  | Story Points: 2 | 8
Story Points: 1 | 4
Assumptions Made
Advanced Output |  |  |  | Write tests | 1
Write tests | 1 |  |  | Add assumptions where applicable | 2.5
Make all relevant information visible | 2.5 |  |  | Run tests | 0.5
Run tests | 0.5 |  |  | Story Points: 1 | 4
Story Points: 1 | 4
Expected Solar Generation
Break Even Point |  |  |  | Write tests | 1
Write tests | 1 |  |  | Format output accordingly | 2.5
Implement calculations | 1.5 |  |  | Run tests | 0.5
Format output | 1 |  |  | Story Points: 1 | 4
Run tests | 0.5
Story Points: 1 | 4

## Charts
Velocity: 10